Goal: Ensure clear responsibilities, safety, and quality of work

## 1. Manpower (People & Roles)

- Event leadership team (Paul)

  - Overall coordinator (runs schedule + decisions)

  - Build station leads (1 per station)

- Volunteers

  - Measurements/cutting team

  - Sanding/prep team

  - Drilling Team

  - Assembly Team

  - Quality control team

  - Branding Team

  - Staining Team

- Support roles

  - Load-in / load-out teams

  - Runners (move tools/materials between stations)

  - Check-in leader / administration (pre-build)

- Recruiting

  - Supplied by Ed & Ethel Jewelry

  - Regular Volunteers from SHP-NRV

  - VT Group Volunteers (if needed)

## 2. Materials & Supplies

Goal: Have everything on-site before volunteers arrive

- Core build materials

  - Wood

  - Vinegar + steel wool stain

  - Screws

  - Dunk tank

- Tools

  - Power drills + extra batteries + chargers

  - Drill press

  - Impact driver

  - Orbital sander

  - Hammers

  - Measuring tape

  - Firepit + Branding irons

  - Welded metal frames for drilling holes

- Safety gear

  - Safety glasses

  - Gloves

  - First aid kit

- Consumables

  - Sandpaper

  - Vinegar + steel wool mix

- Material Planning

  - Wood (ordered two weeks before build)

  - Vinegar + steel wool mixture (prepped before event)

## 3. Logistics & Site Setup

Goal: Turn venue into efficient build environment

- Layout planning:

  - Assembly line stations (Step 1 → Step 2 flow)

  - Separate zones for tools, materials, finished beds

  - Check-in + briefing area (Pre-build)

- Physical setup:

  - Tables/workbenches

  - Tool stations at each build zone

- Flow design:

  - One-direction build flow to avoid congestion

  - “Finished product” staging area

- Location Contingency

  - If weather or location is not suitable for build, we will move to parking garage behind Truist

## 4. Transportation & Movement

Goal: Ensure materials and finished beds move efficiently

- Pickup/delivery of materials before event

- Vehicle(s) for transporting beds post-build

- Loading/unloading crew schedule

- Designated staging area for load-out

## 5. Timeline & Execution Plan

Goal: Keep event on schedule and avoid bottlenecks

- Setup window (before volunteers arrive, typically 1 hour before the build)

- Volunteer check-in + safety briefing

- Build station manned

- Build commences

- Finish build

- Cleanup + teardown window

- Delivery to storage location

## 6. Communication & Coordination

Goal: Keep everyone informed and aligned

- Pre-event:

  - Volunteer signup + reminders

  - Instructions / what to wear / expectations

- Day-of:

  - Role assignments for volunteers

  - Group announcements

## 8. Quality Control (QC)

Goal: Ensure beds are safe and usable

- Inspection after each build stage

- Final structural check before moving to “finished” area

- Standard checklist (tightness, alignment, stability)

- Drill holes for bolts and pegs

## 9. Post-Event Wrap-Up

Goal: Clean site and confirm delivery readiness

- Breakdown and cleanup crew

- Tool inventory check (ensure nothing missing)

- Waste disposal

- Final bed count verification

- Transportation to storage facility

- Debrief notes for next event improvement