# Project Charter – Version 1.0

# Date 2/23/2025

| Project Title: Dream Builders |  |  |
| --- | --- | --- |
| Project Start Date: 1/29/2025 Projected Finish Date: 5/5/2026 |  |  |
| Projected Budget Information: (If Applicable) - Printing costs for Marketing Flyers |  |  |
| Project Manager: Holden Crouse, (540) 820-7522, hbcrouse05@vt.edu |  |  |
| Project Objectives/Goals: Fundraise 40 Bed-in-a-bags before April 25th bed build and build 40 beds during April 25th bed build |  |  |
| Constraints, Assumptions, Risks and Dependencies (when applicable) Constraints: - Inability to find organizations to fundraise - Low amount of volunteers - Delays in material delivery - Limited personal capital to raise bedding on our own Assumptions: - Existing bed build sponsor experience - Indoor parking garage for bed build in case of bad weather - Volunteers to complete the bed build on April 25th Risks and Dependencies: - We need to fundraise 40 Bed-in-a-bags before the bed build - Bed build could be cancelled or delayed until after the semester ends - Sponsor provides bed build materials |  |  |
| Approval Signatures |  |  |
| Name and Signature | Role/Stakeholder | Contact Information |
| Paul Mele | Project Sponsor | paul.mele@shpbeds.org |
| Holden Crouse | Project Manager | hbcrouse05@vt.edu |
| Asher Tilghman | Group Member | ashertilghman@vt.edu |
| Andres Vasquez | Group Member | andresv84@vt.edu |
| Weijin Tsu | Group Member | weijin@vt.edu |
| Luis Martinez | Group Member | luism@vt.edu |

Email Confirmation for E-Signature