## Slide 1: Probability/Impact Matrix Date
Impact
Probability
low
medium
high
low
medium
high
Not enough volunteers
Weather making it unable to build the beds outside.
Unable to fundraise all 40 bed-in-a-bags
Delay in materials delivery
Poor communication with stakeholders / sponsor

## Slide 2: Mitigation Efforts
Weather prevents bed building outside
  Track the weather for the bed build week and keep volunteers informed of change of build site.
Delay in materials
  Try to order materials ahead of time with sufficient lead times for the bed build.
Unable to fundraise the 40 beds
  Aim to complete fundraising a few weeks before the bed build, so we can figure out alternative solutions. If not on track, we will inform sponsor of the number short of our goal.

## Slide 3: Contingency Plans
Weather make beds unable to be built outside
  Sponsor has arranged for an indoor building site
Delays in bedding shipment
  Cancel shipments and use money to pick up bedding in stores such as Target
Not enough volunteers
  Reach out to friends and classmates to see who would be willing to volunteer
Unable to fundraise bed-in-a-bags
  Inform sponsor far ahead of time if we are not on track to complete the goal, he might be able to use his donations to compensate